## Bidding Calc-Pt 1 (Production)
Bidding Calculator – Part 1
Production Labor Calculator
Position | Wage/hour | Work Days = | 264 | Hours per week | OT markup
Foreperson | 18 |  |  | 40 | 0
Laborer | 12 |  |  | 45 | 6%
Laborer | 12 |  |  | 50 | 10%
Total | 42
42 | 3 | 14
Total wages/hour | x # of crew | = Crew Average Wage
14 | 1 | 14
Crew Average Wage | x 1+overtime factor | = Overtime Rate
14 | 1.12 | 15.68
Overtime Rate | x 1 + risk factor | = Total Crew Average Wage
264 | 15.68 | 4139.52
Total Production Hours | Total Crew Average Wage | Production Labor Cost
Production Material Calculator |  |  |  | Production Subcontractor Calculator
Material Item | Quantity | Per Item Cost | Total | Subcontractor | Cost
24” box trees | 3 | 105 | 315 | Plumber | 1550
15-gallon | 26 | 65 | 1690 | Electrician | 300
Sod (sq ft) | 0 | 2.5 | 0 | Total | 1850
5-gallon | 120 | 28 | 3360
1-gallon | 180 | 8 | 1440 | Production Equipment Cost Calculator
Mulch (yard) | 15 | 22 | 330 | Type of Equipment | Cost Per Hour | Estimated Hours | Total Cost
Irrigation (valve) | 5 | 450 | 2250 | chainsaw | 4 | 2 | 8
Flagstone (sq ft) | 250 | 54 | 13500 | dingo w/bucket | 15 | 22 | 330
Lighting (fixture) | 10 | 275 | 2750 | 6CY dump truck | 20 | 5 | 100
Amendments (yard) | 8 | 96 | 768 |  |  | Total | 438
Fencing (linear ft) | 200 | 28 | 5600
|  | Total | 32003

## Bidding Calc-Pt 2 (General)
Bidding Calculator – Part 2
General Conditions Material Cost Calculator |  |  | General Conditions Subcontractor Cost Calculator
Item | Cost |  | Subcontractor | Cost
Port-a-Potty | 230 |  | Traffic Control
Dump | 480 |  | Rent-a-cop | 768
Permits | 480 |  | Security
Total | 1190 |  | Total | 768
General Conditions Labor Cost Calculator
Non-production activity | Total Wage Rate | Estimated Hours | Total Cost
Supervisor | 32 | 10 | 320
Travel Time | 15.68 | 15 | 235.2
Load/Unload | 15.68 | 7 | 109.76
Warranty | 15.68 | 7 | 109.76
Design | 55 | 9 | 495
Estimating | 55 | 11 | 605
| TOTALS | 59 | 1874.72
General Conditions Equipment Cost Calculator
Type of Equipment | Cost Per Hour | Estimated Hours | Total Cost
Crew Truck ¾ ton | 6 | 104 | 624
Supervisor Truck ½ ton | 5 | 10 | 50
|  | TOTALS | 674
Labor Burden Cost Calculator
4139.52 | 1874.72 | 0.3 | 1804.272 |  | 7818.512
Production Labor Cost | + General Conditions Labor Cost | x Labor Burden Rate | = Labor Burden Cost |  | Total Labor Cost
G&A Overhead Cost Calculator |  |  |  | G&A Overhead Dollars | 100000
5 | 50 | 40 | 10000
Average # of Field Employees Per Year | x Average # of weeks worked | x Average # of hours Worked per week | = Total Field Hours Worked Per Year
100000 | 10000 | 10
G&A Overhead Dollars | ÷ Total Field Labor Hours | = G&A Cost per hour |  |  | ↑ annual
264 | 59 | 10 | 3230 |  | ↓ job
Production Labor Hours | + General Conditions Labor Hours | x G&A Cost per hour | = G&A Overhead Cost
38430.52 | 4506.72 | 1804.272 | 3230 | 47971.512
Production Job Total Cost | + General Conditions Job Total Cost | + Labor Burden Cost | + G&A Overhead Cost | = Breakeven Point
47971.512 | 0.73 | 65714.4
Breakeven Point | ÷ 1 minus Net Profit Margin (27%) | = Final Job Price

## Scenario
Production Labor Calculator
You have determined that it will take you 11 days with a crew of 3 working 8-hour days to install this job. Your labor burden rate is 0.30. You do not work overtime but work a straight 40-hour workweek and your risk factor is 12%.
Production Material Cost Calculator
You will need to figure out all of the material need for this job.
Production Subcontractor Cost
On this project you will need a plumber at $1550 and an electrician for $300 for a total cost of $1850. They both have insurance and you have received their insurance paperwork.
Production Equipment Calculator
You will need to bring equipment in to do this job. You will need a chainsaw for 2 hours to remove some small trees at $4.00/hour. You will need a Dingo with a bucket for 22 hours. You will be using the large dump truck for 5 hours.
General Conditions Material Cost Calculator
You will need to take a port-a-potty to the site for a total of $230. Your permit fees came to $480. Your dump fees cost $480.
General Conditions Subcontractor Cost Calculator
You will need to Rent-a-Cop for 2 8-hour shifts at $48 per hour.
General Conditions Labor Cost Calculator
Your supervisor will be on-site for 7 hours at $25/hour. The crew travel time is 15 hours. The load/unload time is 7 hours for this project. You have 7 hours for warranty and callback work. Your design time came to 9 hours at $55/hour and estimating time was 11 hours at $55/hour.
General Conditions Equipment Cost Calculator
The crew truck is a ¾ ton truck and your supervisor is driving a ½ ton truck.
G & A Overhead Cost Calculator
Your G & A overhead dollars are $100,000 with 5 field employees working 40 hours a week and they get 2 weeks of paid-time-off a year.
You are not bidding against anyone on this project but Mrs. Fiditch can be difficult so you need to build in a hassle-factor of 10%. Your Profit Margin is 22%.