## Production Labor
THIS WORKSHEET IS USED MOSTLY FOR BIDDING CALCULATIONS, BUT ALSO SHOWS COSTING
CALCULATIONS FOR ACCOUNTING COST TRACKING. COSTS INCURRED ARE POSTED TO JOBS AS
WELL AS CLASSES. JOBS SHOW COSTS BY CUSTOMER AND CLASSES SHOW AN ACCUMULATION
OF JOB COSTS BY MAJOR CATEGORY, I.E., RESIDENTIAL, COMMERCIAL, OR CONTRACT MAINT-
ENANCE. CLASSES CAN BE FURTHER DIVIDED BY CUMMULATIVE SQUARE FOOTAGE, I.E., SMALL,
MEDIUM, OR LARGE.
Production Labor Calculator
Position | Wage/Hour |  | Hours per Week | OT Markup
Foreperson | 27.5 |  | 40 | 0%
Laborer | 16.5 |  | 45 | 6%
Laborer | 14 |  | 50 | 10%
Laborer | 12.5
Total | 70.5
70.5 | 4 | 17.625 | 17.63 | 106% | 18.6878
Total Wages/Hour | / # of Crew | = Crew Ave Wage | Crew Average Wage | x 1 + Over-time Factor | = Overtime Rate
|  |  | 18.69 | 112% | 20.9328
|  |  | Overtime Rate | x 1 + Risk Factor | = Total crew ave wage
|  |  | 264 | 20.93 | 5525.52
|  |  | Total Production Hours | Total crew Ave. Wage | Production Labor Cost
Production Labor Calculator
You have determined that it will take nn days with a crew of 3 working 8 hour days to install this
job. Your Labor Burden rate is 30%. You do not work overtime, but work a straight 40-hour
workweek with a Risk Factor of 12%. The Labor Burden Rate and Risk Factor is calculated on the
General Conditions worksheet. (Risk Factor is a contingency [5 - 15%] for labor in case an overrun/
job doesn't go according to plan.)
See Production Equipment Cost Calculator at bottom of General Conditions worksheet.
Production Equipment is a direct hourly charge to the job, not a direct overhead adder. The buyer
who orders the equipment must question the rental agency if there are other associated costs like
insurance and sales taxes to be included in the hourly rates.

## Production Materials
THIS WORKSHEET IS USED MOSTLY FOR BIDDING CALCULATIONS, BUT ALSO SHOWS COSTING
CALCULATIONS FOR ACCOUNTING COST TRACKING. COSTS INCURRED ARE POSTED TO JOBS AS
WELL AS CLASSES. JOBS SHOW COSTS BY CUSTOMER AND CLASSES SHOW AN ACCUMULATION
OF JOB COSTS BY MAJOR CATEGORY, I.E., RESIDENTIAL, COMMERCIAL, OR CONTRACT MAINT-
ENANCE. CLASSES CAN BE FURTHER DIVIDED BY CUMMULATIVE SQUARE FOOTAGE, I.E., SMALL,
MEDIUM, OR LARGE.
Production Material Cost Calculator
Material Item | Quantity | Per Item Cost | TOTAL
24" Box Tree | 9 | 105 | 945
15-Gallon | 20 | 65 | 1300
Sod | 400 Sq Ft | 2.50 sq ft | 1000
5-Gallon | 50 | 28 | 1400
1-Gallon | 100 | 8 | 800
Mulch | 10 Yards | $22.00/yard | 220
Irrigation | 3 Valves | $450/valve | 1350
Flagstone | 250 Sq Ft | $54/sq ft | 13500
Lighting | 10 Fixtures | $275/fixture | 2750
Amendments | 5 Yards | $96/yard | 480
Fencing | 200 Linear feet | $28/linear ft | 5600
|  | TOTAL | 29345
Production Subcontractor Cost
Subcontractor | Cost/Hr
Plumber | 85
Electrician | 115
TOTAL | 200

## General Conditions (DOH)
THIS WORKSHEET IS USED MOSTLY FOR BIDDING CALCULATIONS, BUT ALSO SHOWS COSTING
CALCULATIONS FOR ACCOUNTING COST TRACKING. COSTS INCURRED ARE POSTED TO JOBS AS
WELL AS CLASSES. JOBS SHOW COSTS BY CUSTOMER AND CLASSES SHOW AN ACCUMULATION
OF JOB COSTS BY MAJOR CATEGORY, I.E., RESIDENTIAL, COMMERCIAL, OR CONTRACT MAINT-
ENANCE. CLASSES CAN BE FURTHER DIVIDED BY CUMMULATIVE SQUARE FOOTAGE, I.E., SMALL,
MEDIUM, OR LARGE.
General Conditions Material Cost Calculator
Item | Cost
Port-a-Potty | 55
Dump | 85
Permits | 115
TOTAL | 255
General Conditions Labor Cost Calculator
Non-Production Activity | Total Wage Rate | Estimated Hours (Variable) | Total Cost
Supervisor | 45 |  | 0
Travel Time | 31.845 |  | 0
Load/Unload | 18.69 |  | 0
Warranty | 31.85 |  | 0
Design | 55 |  | 0
Estimating | 37.5 |  | 0
TOTAL
General Conditions Equipment Cost Calculator
Type of Equipment | Cost per Hour | Estimated Hours | Total Cost
Crew Truck 3/4 ton
Supv Truck 1/2 Ton
General Conditions Subcontractor Cost Calculator
Subcontractor | Cost
Traffic Control
Rent-a-Cop
Security
TOTAL
Labor Burden Cost Calculator
Production Labor Cost | + General Conditions Labor Cost | * Labor Burden Rate | = Labor Burden cost
Production Equipment Cost Calculator
Type of Equipment | Cost per Hour | Estimated Hours | Total Cost
TRUCKS:
1/2 Ton Pickup | 5
3/4 Ton Pickup | 6
2 Ton Truck | 12
6 CY Dump Truck | 20
GENERAL EQUIPMENT
Dingo with bucket | 15
Dingo w/o bucket | 25
Mini-Excavator | 25
Rototiller, small | 8
Rototiller, large | 10
Electric jackhammer | 3
Chainsaw | 4
Dumpster | n/a | Deliver & Haul away | 110
TOTAL
The buyer who orders the equipment must question the rental agency if there are other
associated costs like insurance and sales taxes to be included in the hourly rates.

## Gen+Admin OVHD
THIS WORKSHEET IS USED MOSTLY FOR BIDDING CALCULATIONS, BUT ALSO SHOWS COSTING
CALCULATIONS FOR ACCOUNTING COST TRACKING. COSTS INCURRED ARE POSTED TO JOBS AS
WELL AS CLASSES. JOBS SHOW COSTS BY CUSTOMER AND CLASSES SHOW AN ACCUMULATION
OF JOB COSTS BY MAJOR CATEGORY, I.E., RESIDENTIAL, COMMERCIAL, OR CONTRACT MAINT-
ENANCE. CLASSES CAN BE FURTHER DIVIDED BY CUMMULATIVE SQUARE FOOTAGE, I.E., SMALL,
MEDIUM, OR LARGE.
G&A Overhead Cost Calculator
Bedgeted G&A Ovhd Dollars
G&A OVERHEAD Cost Calculator
Ave. # of field employees per year | x Average Nr of Weeks Worked | x Ave. # of hours Worked per Week | = Total field hours worked per year
G & A OVERHEAD Dollars | / Total Field Labor Hours | = G & A OVERHEAD cost per hour
Production Labor Hours | + General Conditions Labor Hours | x G & A OVERHEAD cost per hour | = G & A OVERHEAD COST

## Projection Values
Projection Values for making the example model (prior worksheets) work
Production Cost Calculator:
You have determined that it will take 11 days with a crew of 3 working 8-hour days to install this.
job. Your labor burden rate is 0.30. You do not work overtime but work a straight 40-hour
workweek and your risk factor is 12%
Production Subcontractor Cost:
On this project you will need a plumber at $1,550 and an electricion for $300. They both have
insurance and have provided you with their insurance paperwork.
Production Equipment Calculator:
You will need to bring equipment in to do this job. You will need a chainsaw for 2 hours to
remove some small trees at $4.00/hour. You will need a Dingo with a bucket for 22 hours. You
will need a 6CY dump truck for 5 hours.
General Conditions Cost Calculator:
You will need to take a port-a-potty to the site for a total of $230. Your permit fees came to
$480. Your dump fees cost $480.
General Conditions Cost Calculator:
Your supervisor will be on-site for 7 hours at $25/hour. The crew travel time is 15 hours. The
load/unload time is 7 hours for this project. You have 7 hours for warranty and callback work.
Your design time came to 9 hours at $55/hour and estimating time was 11 hours at $55/hour.
General Conditions Cost Calculator:
The crew truck is a 3/4 ton pickup and your supervisor is driving a 1/2 ton pickup.
General Conditions Cost Calculator:
You will need a Rent-a-Cop for 2-8 hour shifts at $48 per hour.
G & A Overhead Cost Calculator:
Your G & A overhead dollars are $100,000 with 5 field employees working 40 hours per week
and they get 2 weeks paid-time-off a year. You are not bidding against anyone on this project
but Mrs Fiditch can be difficult so you need to build in a hassle-factor of 10%. Your profit
margin is 22%.
The following formula is the last one to be filled in. You need the data from all of the other
formulas to fill in the blanks on the last one.
G&A OVERHEAD Cost Calculator
33488.52 | 5528.72 | 4044.76 | 3200
Project Job Cost Total | x Gen Conditions Cost | x Labor Burden Cost | G & A Overhead Cost
46262 | 46262 | 68% | 68032.3529
= Breakeven Point | Breakeven Point | / 1 minus NetProfit Margin | = Final Job Price

## CofA_SALES + COSTGOODSSOLD
SALES & COSTS OF SALES ACCOUNTS
DEPT NBR | ACCT NBR | SUB-ACCT | DESCRIPTION | ACCT TYPE | STATUS
000 | 4010 |  | SALES ORDER-RESIDENTIAL LANDSCAPING | Sales | A
000 | 4025 |  | SALES ORDER-COMMERCIAL LANDSCAPING | Sales | A
000 | 4040 |  | SALES ORDER-CONTRACTED MAINTENANCE | Sales | A
000 | 4015 |  | SO-ENGINEERING SUPPORT | Sales | I
000 | 4020 |  | SO-MACHINE SALES | Sales | I
000 | 4033 |  | SO-CYBOR PUMPS & SYSTEMS | Sales | I
000 | 4034 |  | SO-PAC SCAN SYSTEMS | Sales | I
000 | 4038 |  | SO-SVG SYSTEMS & PARTS | Sales | I
000 | 4045 |  | SO-REGEN PARTS/SPARES SALES | Sales | I
000 | 4085 |  | RGA-MODULE REPAIRS | Sales | I
000 | 4130 |  | SO-INT'L PARTS/SPARES SALES | Sales | I
000 | 4170 |  | FS-INT'L FIELD SERVICE | Sales | I
000 | 4180 |  | RGA-INT'L PC BD REPAIRS | Sales | I
000 | 5010 |  | COS-PLANT MATERIALS | COGS | A
|  | 5011 | TREES & HEDGES | COGS | A
|  | 5014 | POTTED PLANTS | COGS | A
|  | 5017 | SOD | COGS | A
|  |  |  | COGS | A
|  |  |  | COGS | A
000 | 5025 |  | COS-SOIL ADDITIVES | COGS | A
|  | 5026 | RECYCLED SOIL | COGS | A
|  | 5029 | SAND | COGS | A
|  | 5030 | MULCH, BARK, & AMMENDMENTS | COGS | A
|  | 5032 | FLAGSTONE | COGS | A
|  | 5035 | STEPPING & DECORATIVE STONES | COGS | A
|  | 5037 | FERTILIZER (MOSTLY ORGANIC), COMPOST | COGS | A
|  | 5039 | SOIL TESTS | COGS | A
000 | 5040 |  | COS-CONCRETE ADDITIVES | COGS | A
|  | 5041 | PAVING | COGS | A
|  | 5045 | BLOCKS | COGS | A
|  | 5049 | AGGREGATE OR CRUSHED ROCK/CONCRETE | COGS | A
000 | 5055 |  | COS-WOOD ADDITIVES | COGS | A
|  | 5056 | FENCING | COGS | A
|  | 5060 | PLANTERS | COGS | A
|  | 5064 | DECKS & STAIRS | COGS | A
|  | 5068 | STORAGE SHEDS | COGS | A
000 | 5070 |  | COS-GREYWATER ADDITIVES | COGS | A
|  | 5071 | CATCH BASINS | COGS | A
|  | 5075 | PVC LINES | COGS | A
|  | 5079 | OTHER | COGS | A
000 | 5085 |  | COS-IRRIGATION & DRAINAGE | COGS | A
|  | 5086 | PVC LINES | COGS | A
|  | 5090 | SPRINKLER HEADS, DRIP ATTACH | COGS | A
|  | 5094 | SOIL OR ROCKS | COGS | A
000 | 5100 |  | COS-LIGHTING & OTHER FIXTURES | COGS | A
|  | 5101 | ELECTRICAL WIRES | COGS | A
|  | 5105 | FIXTURES | COGS | A
| 5150 |  | DIRECT LABOR | COGS | A
|  | 5151 | DIR LAB-PLANT MATERIALS | COGS | A
|  | 5153 | DIR LAB-SOIL ADDITIVES | COGS | A
|  | 5155 | DIR LAB-CONCRETE ADDITIVES | COGS | A
|  | 5157 | DIR LAB-WOOD ADDITIVES | COGS | A
|  | 5159 | DIR LAB-GREYWATER ADDITIVES | COGS | A
|  | 5161 | DIR LAB-IRRIGATION & DRAINAGE | COGS | A
|  | 5163 | DIR LAB-LIGHTING & OTHER FIXTURES | COGS | A
| 5175 |  | SUPERVISORY LABOR | COGS | A
|  | 5176 | SUPV LAB-PLANT MATERIALS | COGS | A
|  | 5178 | SUPV LAB-SOIL ADDITIVES | COGS | A
|  | 5180 | SUPV LAB-CONCRETE ADDITIVES | COGS | A
|  | 5182 | SUPV LAB-WOOD ADDITIVES | COGS | A
|  | 5184 | SUPV LAB-GREYWATER ADDITIVES | COGS | A
|  | 5186 | SUPV LAB-IRRIGATION & DRAINAGE | COGS | A
|  | 5188 | SUPV LAB-LIGHTING & OTHER FIXTURES | COGS | A
| 5195 |  | CONTRACT LABOR | COGS | A
|  | 5196 | CONT LAB-PLANT MATERIALS | COGS | A
|  | 5198 | CONT LAB-SOIL ADDITIVES | COGS | A
|  | 5200 | CONT LAB-CONCRETE ADDITIVES | COGS | A
|  | 5202 | CONT LAB-WOOD ADDITIVES | COGS | A
|  | 5204 | CONT LAB-GREYWATER ADDITIVES | COGS | A
|  | 5206 | CONT LAB-IRRIGATION & DRAINAGE | COGS | A
|  | 5208 | CONT LAB-LIGHTING & OTHER FIXTURES | COGS | A
| 5210 |  | GENERAL CONDITIONS COST FACTORS | COGS | A
|  | 5211 | GENERAL CONDITIONS MATERIAL COSTS | COGS | A
|  | 5215 | GENERAL CONDITIONS LABOR COSTS | COGS | A
|  | 5219 | GENERAL CONDITIONS EQUIPMENT COSTS | COGS | A
|  | 5223 | GENERAL CONDITIONS SECURITY COSTS | COGS | A
| 5225 |  | PRODUCTION EQUIPMENT COSTS | COGS | A
|  | 5226 | TRUCKS | COGS | A
|  | 5230 | GENERAL EQUIPMENT | COGS | A
| 5240 |  | LABOR BURDEN COST ABSORBTION | COGS | A
| 5250 |  | G & A COST ABSORBTION | COGS | A
000 | 5110 |  | COS-MATERIAL USAGE VARIANCE | COGS | A
000 | 5115 |  | COS-ASSEMBLY BENCH STOCK | COGS | A
000 | 5116 |  | COS-RMA BENCH STOCK (TAXABLE) | COGS | A
000 | 5118 |  | COS-SCRAPPED MATERIAL | COGS | A
000 | 5119 |  | COS-MATERIALS, OTHER VARIANCES | COGS | A
000 | 5120 |  | COS-LABOR EFFICIENCY VARIANCE | COGS | A
000 | 5121 |  | COS-LABOR APPLIED TO CLOSE JOBS | COGS | A
000 | 5130 |  | COS-OVRHEAD EFFICIENCY VARIANCE | COGS | A
000 | 5145 |  | COS-NON-STD OUTSIDE PROCESSING | COGS | A
000 | 5150 |  | EARNED MFG OVERHEAD | COGS | A
000 | 5151 |  | ACTUAL MFG OVERHEAD-MFG ASSY | COGS | A
000 | 5152 |  | ACTUAL MFG OVERHEAD-PCB/MOD REP | COGS | A
000 | 5153 |  | ACTUAL MFG OVERHEAD-MFG ADMIN | COGS | A
000 | 5154 |  | ACTUAL MFG OVERHEAD-INV CONTROL | COGS | A
000 | 5155 |  | ACTUAL MFG OVERHEAD-PURCHASING | COGS | A
000 | 5156 |  | ACTUAL MFG OVERHEAD- | COGS | A
000 | 5160 |  | EARNED SVC OVERHEAD | COGS | A
000 | 5162 |  | ACTUAL MFG OVERHEAD-SC CUST SVC | COGS | A
000 | 5164 |  | ACTUAL MFG OVERHEAD-PA CUST SVC | COGS | A
000 | 5165 |  | ACTUAL MFG OVERHEAD-AZ CUST SVC | COGS | A
000 | 5200 |  | COS-SO-GCA SYSTEM SALES | COGS | A
000 | 5210 |  | COS-SO-GCA REGENERATION | COGS | A
000 | 5220 |  | COS-SO-GCA UPGRADES | COGS | A
000 | 5230 |  | COS-SO-GCA PCB REPAIRS | COGS | A
000 | 5240 |  | COS-SO-GCA MODULE REPAIRS | COGS | A
000 | 5250 |  | COS-SO-GCA FIELD SERVICE | COGS | A
000 | 5260 |  | COS-SO-GCA SPARE PARTS | COGS | A
000 | 5300 |  | COS-SO-SVG SYSTEM SALES | COGS | A
000 | 5310 |  | COS-SO-SVG EGENERATION | COGS | A
000 | 5320 |  | COS-SO-SVG UPGRADES | COGS | A
000 | 5330 |  | COS-SO-SVG PCB REPAIRS | COGS | A
000 | 5340 |  | COS-SO-SVG MODULE REPAIRS | COGS | A
000 | 5350 |  | COS-SO-SVG FIELD SERVICE | COGS | A
000 | 5360 |  | COS-SO-SVG SPARE PARTS | COGS | A
000 | 5400 |  | COS-SO-MILLEN 2000 SYSTEM SALES | COGS | A
000 | 5410 |  | COS-SO-MILLEN 2000 REGENERATN | COGS | A
000 | 5420 |  | COS-SO-MILLEN 2000 UPGRADES | COGS | A
000 | 5430 |  | COS-SO-MILLEN 2000 PCR REPAIRS | COGS | A
000 | 5440 |  | COS-SO-MILLEN 2000 MODULE REPAIR | COGS | A
000 | 5450 |  | COS-SO-MILLEN 2000 FIELD SERVICE | COGS | A
000 | 5460 |  | COS-SO-MILLEN 2000 SPARE PARTS | COGS | A
000 | 5770 |  | WARRANTY REPAIR | COGS | A
000 | 5803 |  | BOOK-TO-PERPETUAL ADJUSTMENT | COGS | A
000 | 5806 |  | TERMS/PURCHASE DISCOUNTS | COGS | A
000 | 5807 |  | SALES DISCOUNTS | COGS | A
000 | 5808 |  | ACCTS REC FINANCE CHARGE | COGS | A
000 | 5809 |  | SALES TAX EXPENSE | COGS | A
000 | 5810 |  | PHYSICAL INVENTORY ADJUSTMENT | COGS | A
000 | 5820 |  | STANDARD COST REVISION ADJUST | COGS | A
000 | 9130 |  | INTEREST INCOME | Misc | A
000 | 9140 |  | INTEREST EXPENSE | Misc | A
000 | 9170 |  | BAD DEBT WRITE-OFF | Misc | A
000 | 9180 |  | EXTRAORDINARY ITEMS | Misc | A
000 | 9510 |  | PROVISION FOR STATE INCOME TAXES | Misc | A
000 | 9520 |  | PROVISION FOR FEDRL INCOME TAXES | Misc | A
000 | 5015 |  | COS-SO-ENGINEERING SUPPORT | COGS | I
000 | 5020 |  | COS-SO-MACHINE SALES | COGS | I
000 | 5033 |  | COS-SO-CYBOR PUMPS & SYSTEMS | COGS | I
000 | 5034 |  | COS-SO-PAC SCAN SYSTEMS | COGS | I
000 | 5038 |  | COS-SO-SVG PARTS | COGS | I
000 | 5045 |  | COS-SO-REGEN PARTS/SPARES SALES | COGS | I
000 | 5075 |  | COS-FS-APPLICATION SUPPORT | COGS | I
000 | 5140 |  | MFG OVERHEAD VARIANCE | COGS | I
000 | 5141 |  | CUST. SVC. OVERHEAD VARIANCE | COGS | I
000 | 5710 |  | WARRANTY REPAIR - CONT. MAINT. | COGS | I
000 | 5715 |  | WARRANTY REPAIR - ENGNRG SUPPT | COGS | I
000 | 5720 |  | WARRANTY REPAIR - MACHINE SALE | COGS | I
000 | 5730 |  | WARRANTY REPAIR - PARTS/SPARES | COGS | I
000 | 5740 |  | WARRANTY REPAIR - REGENERATION | COGS | I
000 | 5775 |  | WARRANTY REPAIR - APPLCN SUPPT | COGS | I
000 | 5780 |  | WARRANTY REPAIR - RGA PC BOARD | COGS | I
000 | 5785 |  | WARRANTY REPAIR - RGA MODULES | COGS | I
000 | 5805 |  | CYCLE COUNT ADJUSTMENT | COGS | I
Note on F2: Gerald Hunt: A = Active, I = Inacrive